## ER Description
Exchange Requirement | S1. Project Scheduling Report | Exchange Requirement | S2. Complete Sign Design - PDF | Exchange Requirement | S3. Signs Requirements and Specifications | Exchange Requirement | S4. Shop Drawings | Exchange Requirement | S5. Approved/Rejected Shop Drawings with comments | Exchange Requirement | S6. Sign Installation Requirements and Specifications | Exchange Requirement | S7. Signs | Exchange Requirement | S8. As-Built Drawings and Documents
Project Stage | Planning and Programming | Project Stage | Final Design | Project Stage | Final Design | Project Stage | Final Design | Project Stage | Final Design | Project Stage | Advertising and Letting | Project Stage | Construction | Project Stage | Postconstruction
Exchange Disciplines | 1. All Design Offices 2. Sign Design Team | Exchange Disciplines | 2. Sign Design Team 3. Contracts Office | Exchange Disciplines | 2. Sign Design Team 4. Sign Fabricator | Exchange Disciplines | 4. Sign Fabricator 2. Sign Design Team | Exchange Disciplines | 2. Sign Design Team 4. Sign Fabricator | Exchange Disciplines | 3. Contracts Office 5. Contractor | Exchange Disciplines | 4. Sign Fabricator 5. Contractor | Exchange Disciplines | 5. Contractor 6. District Engineer
Description | The Project Scheduling Report comprises the list of preconstruction and construction activities (events) required to complete the project. Information provided about each activity includes: - Event Description - Project Number - Expected Duration - Expected Start Date - Expected Finish Date - Expected Number of Work Hours | Description | The final sign design must be compressed into a single PDF file and submitted to the Contracts Office. The PDF file must follow Iowa DOT's standard requirements. This file includes the sign installation requirements and specifications to be included in the contract. | Description | Sign requirements and specifications are sent to the sign fabricator in order for it to proceed with the development of the shop drawings. If requested by the sign fabricator, requirements and specifications may be submitted with the original MicroStation design file. | Description | Shop drawings developed by the fabricator must be in accordance with the requirements and specifications prepared by the sign design team. Shop drawings must be submitted to the sign design team for review and approval before proceeding with fabrication. | Description | Approved or rejected shop drawings are sent back to the sign fabricator, with comments as applicable. If approved, the fabricator must address all the design team's comments before proceeding with fabrication. If rejected, the fabricator must address all the design team's comments, redevelop the shop drawings, and resubmit them for review and approval. | Description | Sign installation requirements and specifications are included in the contract to be used by the contractor during construction. | Description | Once signs are fabricated, they are sent to an Iowa DOT's storage facility, where they are picked up by the contractor. | Description | As-built drawings and documents must be sent to the district engineer by the contractor. The design engineer must use this information to update the sign inventory.